## Document Control
Abstract: |  | Test Case Design
Template ID |  | QTIN-TMP-DER | Ver.No |  | 1
Project Name
Project ID
Commercial |  | This document is the sole property of QualiTest India and shall not be reproduced / Photocopied either partly or wholly without approval of the Head, QTSF
Document Classification |  | Commercial in Confidence
Document Change History
S/N | Description |  |  | Date | Author | Ver. No.
1
2
3
4
5

## Defect Report
Project Name |  | QTRecognition
Project ID |  | Qt1
Build/Release Version |  | <<Release version of the product. (e.g. 1.2.5)>>
Defect ID | Module | Build Version | Reported by | Reported Date | Defect Description | Steps to Reproduce | Severity | Status | Fixed in Build | Remarks/Attachments
D-01 | Verification |  | Usha s | 2021-11-03 | while entering username and password the forward action should not work but it is working | 1. enter the username 2. click on forward arrow | critical | New |  | https://ibase1-my.sharepoint.com/:i:/r/personal/usha_suresh_qualitestgroup_com/Documents/Screenshot%20(4).png?csf=1&web=1&e=vYGZ6w
D-02 | verification |  | Usha s | 2021-11-03 | while entering password it should not go backward | 1. enter the password 2. click on go back | critical | New |  | https://ibase1-my.sharepoint.com/:i:/r/personal/usha_suresh_qualitestgroup_com/Documents/Screenshot%20(6).png?csf=1&web=1&e=4U6eRl
D-03 | Verification |  | Usha s | 2021-11-03 | if invalid username and password is entered it should display error message but it is redirect backword/forward | 1.enter the invalid username and password. 2.click on go back/forward | critical | New |  | https://ibase1-my.sharepoint.com/:i:/r/personal/usha_suresh_qualitestgroup_com/Documents/Screenshot%20(6).png?csf=1&web=1&e=4B4nOZ
D-04 | Search Kudos |  | Usha s | 2021-11-03 | when we enter the invalid recepient name it should display errormessage but the activity page remains constant | 1.click on the search kudos option 2.enter the invalid recepient name 3.click on search symbol | major | New |  | https://ibase1-my.sharepoint.com/:i:/r/personal/usha_suresh_qualitestgroup_com/Documents/search%20kudos%20(2).png?csf=1&web=1&e=22igaX

## Guidelines
Defect ID: | Severity (Critical/Major/Minor):
Unique ID is required for each defect. Follow some convention to indicate types of the test. E.g. ‘BUG_UI_1’ indicating ‘user interface bug #1’. | Critical: The defect affects critical functionality or critical data. It does not have a workaround. Example: Unsuccessful installation, complete failure of a feature. Major: The defect affects major functionality or major data. It has a workaround but is not obvious and is difficult. Example: A feature is not functional from one module but the task is doable if 10 complicated indirect steps are followed in another module/s. Minor: The defect affects minor functionality or non-critical data. It has an easy workaround. Example: A minor feature that is not functional in one module but the same task is easily doable from another module.
Module Name: | Defect Description
Mention the name of the main module or the sub-module. | Description of the defect explaining the problem in detail scenario, frequency, field/screen etc.
Build Version | Steps to Reproduce
Mention the version of the application under test. | List the user actions step by step so that the developer can reproduce the issue as easy.
Reported by | Fixed in Build
Name of the tester who discovered the defect. | Mention the version of the build number in which the defect was regressed and found fixed.
Reported date | Status (New,Open,Closed, Assigned,Deferred):
Actual date when the defect was reported. | Update the status when the defect status as and when there is a changes as per defect lifecycle.